## TOP
WK | SUB 1 | SUB 2 | Task Name | kV | Duration | Start | Finish
2 | TANDRAGEE |  | BUS ZONE (PROJECTS) - PROTECTION CHANGE | 275 | 5 wks | 2021-01-04 | 2021-02-05 | 2021-02-16
2 | BALLYLUMFORD | KELLS | BPS-KEL PROTECTION CHANGE | 275 | 8 wks | 2021-01-04 | 2021-02-26
3 | CASTLEREAGH | BALLYNAHINCH 'B' | CAS-BNH B PROTECTION WORK | 110 | 5 wks | 2021-01-11 | 2021-02-12
3 | HANNAHSTOWN | IBTX1 | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT | 110 | 4 wks | 2021-01-11 | 2021-02-05
4 | LIMAVADY |  | TX2 33KV CABLE TEMPORARY DISCONNECTION FOR PRECONSTRUCTION CIVIL WORKS | 110 | 2 wks | 2021-01-18 | 2021-01-29
4 | MAGHERAFELT |  | Bus-zone 3 zone | 275 | 5 wks | 2021-01-18 | 2021-02-19
6 | LIMAVADY |  | TX1 33KV CABLE TEMPORARY DISCONNECTION FOR PRECONSTRUCTION CIVIL WORKS | 110 | 2 wks | 2021-02-01 | 2021-02-12
6 | TREMOGE |  | PQ MONITORS | 110 | 3 days | 2021-02-05 | 2021-02-09
7 | HANNAHSTOWN | IBTX2 | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT | 110 | 4 wks | 2021-02-08 | 2021-03-05
7 | KILLYMALLAGHT | COOLKEERAGH | KMT-CPS POLE REPLACEMENTS WORKS | 110 | 1 wk | 2021-02-08 | 2021-02-12
8 | LIMAVADY |  | PRE CONSTRUCTION COLERAINE CVTS BASE PROXIMITY | 110 | 2 wks | 2021-02-15 | 2021-02-26
8 | KILLYMALLAGHT | STRABANE | KMT-STR POLE REPLACEMENTS WORKS | 110 | 2 wks | 2021-02-15 | 2021-02-26
9 | KILROOT |  | Bus-zone 3 zone | 275 | 5 wks | 2021-02-22 | 2021-03-26
10 | TANDRAGEE | DRUMNAKELLY 'A' | TAN-DRU A PROTECTION CHANGE | 110 | 5 wks | 2021-03-01 | 2021-04-02
10 | LIMAVADY |  | PRE CONSTRUCTION COOLKEERAGH CVTS BASE PROXIMITY | 110 | 2 wks | 2021-03-01 | 2021-03-12
10 | KELLS |  | CIRCUIT BREAKER FAILS SCHEME ( 4 SETS ) | 275 | 6 wks | 2021-03-01 | 2021-04-09
10 | STRABANE | OMAGH 'A' | STR-OMA A POLE REPLACEMENTS WORKS | 110 | 1 wk | 2021-03-01 | 2021-03-05
10 | CASTLEREAGH | TANDRAGEE | CAS-TAN OHL WORKS AND TOWER PAINTING | 275 | 2 wks | 2021-03-01 | 2021-03-12
11 | HANNAHSTOWN | DONEGALL 'B' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT | 110 | 5 wks | 2021-03-08 | 2021-04-09
11 | STRABANE | OMAGH 'B' | STR-OMA B POLE REPLACEMENTS WORKS | 110 | 2 wks | 2021-03-08 | 2021-03-19
13 | DONEGALL | HANNAHSTOWN | DON CABLE OIL FLUSHING WORKS (A' CIRCUIT OIL LEAK REPAIRS) - OIL WORKS | 110 | 1 day | 2021-03-22 | 2021-03-22
13 | COLERAINE | RASHARKIN | COL-RSK POLE REPLACEMENTS WORKS | 110 | 2 wks | 2021-03-22 | 2021-04-02
13 | DONEGALL |  | DONEGALL TX C (PROJECTS) - TRANSFORMER PAINTING & Major Maintenance | 110 | 4 wks | 2021-03-22 | 2021-04-16
13 | KELLS | RASHARKIN | KEL-RSK POLE REPLACEMENTS WORKS | 110 | 2 wks | 2021-03-22 | 2021-04-02
14 | DRUMNAKELLY |  | DRU (TX1 & TX3 TAPCHANGER PANELS) - PROJECTS | 110 | 4 wks | 2021-03-29 | 2021-04-23
14 | LIMAVADY |  | mesh refurbishment 1ST CORNER, TX2, 53V0 REPLACEMENT,52V8,53V4 & CX193. | 110 | 8 wks | 2021-03-29 | 2021-05-21
14 | CASTLEREAGH | KNOCK 'A' | CAS-KNO A (PROJECTS) - CABLE DIVERSION WORK | 110 | 6 wks | 2021-03-29 | 2021-05-07
14 | KILROOT |  | CIRCUIT BREAKER FAILS SCHEME ( 13 SETS ) | 275 | 6 wks | 2021-03-29 | 2021-05-07
15 | MAGHERAFELT | TAMNAMORE 'A' | TMN- MAG 'A' (OHL WORK) - SINGLE TENSION TOWER 228 | 275 | 5 days | 2021-04-05 | 2021-04-09
15 | OMAGH | GORT | (PQ monitors) - OMA-GRT | 110 | 3 days | 2021-04-05 | 2021-04-07
15 | CASTLEREAGH |  | CASTLEREAGH MAIN INTERBUS T1 (275/110) - Major Maintenance | 275 | 3 wks | 2021-04-05 | 2021-04-23
15 | TANDRAGEE |  | TANDRAGEE MAIN INTERBUS 1 MAJOR MAINTENANCE | 275 | 3 wks | 2021-04-05 | 2021-04-23
15 | COOLKEERAGH | MAGHERAFELT | CPS - MAG A PROTECTION CHANGE (PROTECTION UPGRADE) - PROJECT WORK | 275 | 10 wks | 2021-04-05 | 2021-06-11
15 | COOLKEERAGH | MAGHERAFELT | CPS - MAG 'A' (OHL WORK) - OHL WORK | 275 | 2 wks | 2021-04-05 | 2021-04-16
16 | HANNAHSTOWN | DONEGALL 'A' | HANNAHSTOWN 110KV ISOLATOR REPLACEMENT | 110 | 5 wks | 2021-04-12 | 2021-05-14
16 | HANNAHSTOWN | DONEGALL 'A' | HAN - DON A CABLE FAULT (OIL WORKS) - REPAIRS | 110 | 1 day | 2021-04-12 | 2021-04-12
17 | COOLKEERAGH | COLERAINE | CPS-COL POLE REPLACEMENTS WORKS | 110 | 2 wks | 2021-04-19 | 2021-04-30
18 | DRUMQUIN |  | PQ MONITORS | 110 | 3 days | 2021-04-27 | 2021-04-29
18 | DROMORE |  | PQ MONITORS | 110 | 3 days | 2021-04-30 | 2021-05-04
19 | LARNE |  | LARNE TX1 BUSHINGS (PROJECTS) - BUSHING CHANGES AND TAPCHANGER REPAIR | 110 | 3 wks | 2021-05-03 | 2021-05-21
19 | HANNAHSTOWN | LISBURN 'B' | HAN-LIS B HOUSING DEVELOPMENT POLES (HAN - LIS 'B') - POLE CHANGES | 110 | 5 days | 2021-05-03 | 2021-05-07
19 | BALLYLUMFORD |  | IBTX1 EARTHING TX AND COOLERS | 275 | 3 wks | 2021-05-03 | 2021-05-21
19 | COOLKEERAGH | SPRINGTOWN 'A' | CPS - SPR 'A' (OHL WORK) - TOWER PAINTING | 110 | 1 wk | 2021-05-03 | 2021-05-07
19 | DONEGALL |  | TX 'B' Maintenance | 110 | 3 wks | 2021-05-03 | 2021-05-21
20 | HANNAHSTOWN | LISBURN 'A' | HAN-LIS A ROAD POLE DIVERSIONS (HAN - LIS 'A') - POLE CHANGES | 110 | 5 days | 2021-05-10 | 2021-05-14
20 | TANDRAGEE | DRUMNAKELLY 'A' | TAN - DRU A (OHL WORK) - | 110 | 2 wks | 2021-05-10 | 2021-05-21
20 | KILROOT | CASTLEREAGH | KPS-CAS OHL WORKS AND TOWER PAINTING | 275 | 2 wks | 2021-05-10 | 2021-05-21
20 | COLERAINE | LOGUESTOWN 'B' | COL-LOG B tower painting | 110 | 1 wk | 2021-05-10 | 2021-05-14
20 | CASTLEREAGH | KNOCK 'B' | CAS-KNO B (PROJECTS) - CABLE DIVERSION WORK | 110 | 6 wks | 2021-05-10 | 2021-06-18
20 | COOLKEERAGH | SPRINGTOWN 'B' | CPS - SPR 'B' (OHL WORK) - TOWER PAINTING | 110 | 1 wk | 2021-05-10 | 2021-05-14
20 | BELFAST NORTH MAIN | DONEGALL | DONEGALL - BELFAST NORTH MAIN CABLE WORKS - CSE REPLACEMENTS | 110 | 1 wk | 2021-05-10 | 2021-05-14
20 | BELFAST NORTH MAIN | DONEGALL | B' CIRCUIT OILWORKS, cable identification & leak repairs | 110 | 2 wks | 2021-05-10 | 2021-05-21
21 | KILROOT |  | KPS CT CHANGE BAY 3 CT'S gj44 side of GJ45(PROJECTS) - CT REPLACEMENT BAY (also GJ45 maint) | 275 | 2 wks | 2021-05-17 | 2021-05-28
21 | HANNAHSTOWN | DONEGALL - BELFAST NORTH 'A' | HAN - DON - BNM A (PROJECTS) - 3 ENDED PROTECTION | 110 | 6 wks | 2021-05-17 | 2021-06-25
22 | LARNE |  | LARNE TX2 BUSHINGS (PROJECTS) - BUSHING CHANGES | 110 | 3 wks | 2021-05-24 | 2021-06-11
22 | KILROOT | TANDRAGEE | KPS-TAN OHL WORKS AND TOWER PAINTING | 275 | 2 wks | 2021-05-24 | 2021-06-04
22 | TANDRAGEE | NEWRY 'A' | TAN-NEW A Tower Painting | 110 | 1 wk | 2021-05-24 | 2021-05-28
22 | LIMAVADY |  | mesh refurbishment 2ND CORNER, TX1,52V0 REPLACEMENT,52V4,51V8 & CX196 | 110 | 8 wks | 2021-05-24 | 2021-07-16
22 | BALLYLUMFORD |  | IBTX2 EARTHING TX AND COOLERS | 275 | 3 wks | 2021-05-24 | 2021-06-11
23 | TANDRAGEE | NEWRY 'B' | TAN - NRY B (PROJECTS) - TELEPROTECTION CHANGE AND DISTANCE PROTECTION | 110 | 5 wks | 2021-06-01 | 2021-07-05
23 | TANDRAGEE | NEWRY 'B' | TAN - NRY B (TOWER PAINTING ) - TOWER PAINTING | 110 | 2 wks | 2021-06-01 | 2021-06-14
23 | TANDRAGEE |  | TANDRAGEE REACTOR '3' INSTALLATION | 275 | 6 wks | 2021-06-01 | 2021-07-12
24 | ENNISKILLEN |  | ENNISKILLEN MAIN T1 (110/33) (TX1 COOLER REPAIRS) - OIL LEAK REPAIRS | 110 | 2 wks | 2021-06-07 | 2021-06-18
24 | BALLYLUMFORD | MAGHERAFELT | BPS-MAG TROLLEY WORKS AND TOWER PAINTING | 275 | 1 wk | 2021-06-07 | 2021-06-11
24 | EDEN |  | TRANSFORMER '1' (110KV BUSHING REPLACEMENT) - plus coolers | 110 | 1 wk | 2021-06-07 | 2021-06-11
24 | CASTLEREAGH | RATHGAEL 'A' | CAS - RAT A (PROJECTS) - DISTANCE PROTECTION | 110 | 5 wks | 2021-06-07 | 2021-07-09
24 | RATHGAEL |  | TX1 COOLERS REFURB | 110 | 3 wks | 2021-06-07 | 2021-06-25
24 | CASTLEREAGH | RATHGAEL 'A' | CAS - RAT A (OHL WORK) - OHL WORK | 110 | 3 days | 2021-06-07 | 2021-06-09
25 | COOLKEERAGH | MAGHERAFELT | CPS - MAG B PROTECTION CHANGE (PROTECTION UPGRADE) - PROJECT WORK | 275 | 10 wks | 2021-06-14 | 2021-08-20
25 | COOLKEERAGH | MAGHERAFELT | CPS - MAG 'B' (OHL WORK) - OHL | 275 | 2 wks | 2021-06-14 | 2021-06-25
27 | OMAGH | TREMOGE | TRE - OMA ( TREMOGE ) (LINES) - | 110 | 2 wks | 2021-06-28 | 2021-07-09
27 | TREMOGE | OMAGH | TRE - OMA (LINES) - TOWER REPLACEMENT AND LINE DIVERSION | 110 | 4 wks | 2021-06-28 | 2021-07-23
27 | TREMOGE | OMAGH | POLE REPLACEMENTS WORKS | 110 | 2 wks | 2021-06-28 | 2021-07-09
27 | TAMNAMORE | TREMOGE | POLE REPLACEMENTS WORKS | 110 | 2 wks | 2021-06-28 | 2021-07-09
27 | DONEGALL | FINAGHY 'B' | FIN - DON 'B' (OHL WORK) - RESTRINGING | 110 | 2 wks | 2021-06-28 | 2021-07-09
27 | HANNAHSTOWN | DONEGALL - BELFAST NORTH 'A' | HAN - DON - BNM B (PROJECTS) - 3 ENDED PROTECTION | 110 | 6 wks | 2021-06-28 | 2021-08-06
27 | CASTLEREAGH |  | CASTLEREAGH MCXX POLE REPLACEMENT - POLE REPLACEMENT | 110 | 5 days | 2021-07-01 | 2021-07-07
28 | BALLYLUMFORD | BALLYVALLAGH 'A' | BPS-BVG RESTRINGING 65 SPAN | 110 | 3 wks | 2021-07-05 | 2021-07-23
28 | BALLYLUMFORD | BALLYVALLAGH 'A' & 'B' | BPS-BVG A EARTH WIRE 5 D/C OUTAGES 1DAY EACH | 110 | 5 days | 2021-07-05 | 2021-07-09
28 | OMAGH | DROMORE 'A' & 'B' | OMA-DRO trial outage pre 2021 OHL outage | 110 | 2 days | 2021-07-05 | 2021-07-06
28 | ENNISKILLEN | DROMORE 'B' | ENN - DRO B (OHL WORK) - OHL WORK | 110 | 1 wk | 2021-07-06 | 2021-07-12
28 | DONEGALL | FINAGHY 'A' & 'B' | FINAGHY - DONEGALL A & B DOUBLE CIRCUIT EARTH WIRE | 110 | 3 days | 2021-07-10 | 2021-07-13
29 | TAMNAMORE | CREAGH | TMN-CRG POLE REPLACEMENTS WORKS | 110 | 2 wks | 2021-07-12 | 2021-07-23
29 | BALLYCRONANMORE | HANNAHSTOWN | BYC-HAN TROLLEY WORKS AND TOWER PAINTING | 275 | 1 wk | 2021-07-12 | 2021-07-16
29 | OMAGH | DROMORE 'B' | OMA - DRO DC RESTRING PROJECT TRIAL | 110 | 1 day | 2021-07-12 | 2021-07-12
29 | BALLYLUMFORD | BALLYCRONANMORE | fibre optic works | 275 | 1 day | 2021-07-12 | 2021-07-12
29 | KELLS |  | IBTX1 (PROJECTS) - MESH CORNER PROTECTION WORKS (FULL MESH NOT OUT FOR DURATION) | 275 | 8 wks | 2021-07-14 | 2021-09-07
29 | KELLS |  | KEL INTERBUS TRANSFORMER 1 & MAJOR(PROJECTS) - PROTECTION CHANGE (WITH REACTOR) | 275 | 8 wks | 2021-07-14 | 2021-09-07
29 | KELLS |  | KEL REACTOR '1' (PROJECTS) - PROTECTION CHANGE | 275 | 8 wks | 2021-07-14 | 2021-09-07
29 | DONEGALL | FINAGHY 'A' | FIN - DON 'A' (OHL WORK) - RESTRINGING | 110 | 2 wks | 2021-07-14 | 2021-07-27
30 | CASTLEREAGH | RATHGAEL 'B' | CAS - RAT B (PROJECTS) - DISTANCE PROTECTION | 110 | 5 wks | 2021-07-19 | 2021-08-20
30 | CASTLEREAGH | RATHGAEL 'B' | CAS - RAT B (OHL WORK) - OHL WORK | 110 | 3 days | 2021-07-19 | 2021-07-21
30 | COOLKEERAGH | LIMAVADY | POLE REPLACEMENTS WORKS | 110 | 2 wks | 2021-07-19 | 2021-07-30
30 | LIMAVADY |  | mesh refurbishment 3RD CORNER, 51V0 REPLACEMENT ,51V4, 54V8, CX195 AND EV5. (CPS CIRCUIT) | 110 | 8 wks | 2021-07-19 | 2021-09-10
31 | KELLS | BALLYMENA 'A' | KEL-BMA POLE REPLACEMENTS WORKS | 110 | 1 wk | 2021-07-26 | 2021-07-30
31 | BALLYLUMFORD | BALLYVALLAGH 'B' | RESTRINGING 65 SPAN | 110 | 3 wks | 2021-07-26 | 2021-08-13
32 | TANDRAGEE |  | CT RATIO CHANGES 600 - 1000 | 275 | 5 wks | 2021-08-02 | 2021-09-03
32 | KELLS | BALLYMENA 'B' | KEL-BMA POLE REPLACEMENTS WORKS | 110 | 2 wks | 2021-08-02 | 2021-08-13
33 | CASTLEREAGH | HANNAHSTOWN 'B' | HAN - CAS 'B' PROTECTION CHANGE ( PROTECTION UPGRADE) - PROJECT WORK | 275 | 8 wks | 2021-08-09 | 2021-10-01
33 | HANNAHSTOWN |  | 275KV ISOLATORS 2 SETS CASTLEREAGH B GG16,GG17, | 275 | 6 wks | 2021-08-09 | 2021-09-17
35 | MAGHERAFELT |  | GH5 BUS COUPLER PROTECTION UPGRADE | 275 | 5 wks | 2021-08-23 | 2021-09-24
37 | BELFAST AREA |  | sheath voltage limiters and cable flushing circuits tbc | 110 | 4 wks | 2021-09-06 | 2021-10-01
38 | KELLS |  | KEL INTERBUS TRANSFORMER 2 & MAJOR (PROJECTS) - PROTECTION CHANGE | 275 | 8 wks | 2021-09-13 | 2021-11-05
38 | KELLS |  | KEL REACTOR '2' (PROJECTS) - PROTECTION CHANGE AND COOLERS REPLACEMENT | 275 | 8 wks | 2021-09-13 | 2021-11-05
38 | KELLS |  | KEL IBTX '2' (PROJECTS) - MESH CORNER PROTECTION WORKS (FULL MESH NOT OUT FOR DURATION) | 275 | 8 wks | 2021-09-13 | 2021-11-05
38 | LIMAVADY | COLERAINE | COL-LIM POLE REPLACEMENTS WORKS | 110 | 2 wks | 2021-09-13 | 2021-09-24
38 | LIMAVADY |  | mesh refurbishment 4TH CORNER, 54V0 REPLACEMENT,54V4,53V8,CX194 & EV6 (COLERAINE CIRCUIT) | 110 | 8 wks | 2021-09-13 | 2021-11-05
41 | CASTLEREAGH |  | CAS REACTOR 2 REPLACEMENT (PROJECTS) - REACTOR 2 | 275 | 8 wks | 2021-10-04 | 2021-11-26
41 | EDEN |  | TRANSFORMER '2' (110KV BUSHING REPLACEMENT) - plus coolers | 110 | 1 wk | 2021-10-04 | 2021-10-08
41 | TANDRAGEE |  | reactor 3 installation | 110 | 6 wks | 2021-10-04 | 2021-11-12
41 | COOLKEERAGH |  | INTERBUS TRANSFORMER 1 MINOR (INSTALL BUND WALL) - BUND WALL AND BLAST WALL & ETX installation | 275 | 25 days | 2021-10-05 | 2021-11-08
45 | MAGHERAFELT |  | CIRCUIT BREAKER FAILS SCHEME ( 7 SETS ) | 275 | 1 day | 2021-11-01 | 2021-11-01
45 | RASHARKIN | AGIVEY | RSK-AGV (AGIVEY TIE IN) - PROJECTS | 110 | 5 wks | 2021-11-01 | 2021-12-03
45 | RASHARKIN | BROCKAGHBOY | RKN - BKY (AGIVEY TIE IN) - OHL PROJECTS | 110 | 5 wks | 2021-11-01 | 2021-12-03
45 | MAGHERAFELT |  | (CONTROL PANEL REFURBISHMENT) - | 275 | 1 day | 2021-11-02 | 2021-11-02
47 | COOLKEERAGH | STRABANE 'B' | CPS-STR tower painting | 110 | 1 wk | 2021-11-15 | 2021-11-19

## TABLES (hidden)
1 | MONDAY
2 | TUESDAY
3 | WEDNESDAY
4 | THURSDAY
5 | FRIDAY
6 | SATURDAY
7 | SUNDAY